## Sheet1
Key | Feature | Summary | Criteria | Points
LTA-138 | As an admin, I want to configure the Firebase database by following the provided UML diagram, so that the database structure aligns with the system’s requirements and functions efficiently. |  |  | 5
| Configure Firebase Database Based on UML Diagram | Given I am an admin, I want to configure the Firebase database by following the provided UML diagram, so that the database structure aligns with the system’s requirements and functions efficiently. | · Implement the database structure in Firebase as per the attached UML diagram. · Set up collections and documents to match the entities and relationships shown in the UML. · Verify that the database supports the required operations (e.g., create, read, update, delete). · Test the Firebase database setup to ensure it meets the system’s performance and security standards.
LTA-118 | As a customer, I want to be informed if the file I upload exceeds the size limit, so that I can upload a smaller file or take appropriate action. |  |  | 2
| File Size Limitation | Given I am a customer, I want to be informed if the file I upload exceeds the size limit, so that I can upload a smaller file or take appropriate action. | The system supports file uploads up to a specified size limit (e.g., 20 MB). An error message is displayed if the user attempts to upload a file larger than the size limit.
LTA-116 | As a student, I want to see an error message when I upload an unsupported file type, so that I am informed about the file type restrictions and can take corrective action. |  |  | 1
| Error Message for Unsupported File Types | Given I am a student, I want to see an error message when I upload an unsupported file type, so that I am informed about the file type restrictions and can take corrective action. | If a user uploads a file type that is not supported, an error message appears. The error message should clearly state the supported file types.
LTA-127 | As a teacher, I want to quickly copy the translated text, so that I can paste it into other applications. |  |  | 3
| Copy Translated Text | Given I am a teacher, I want to quickly copy the translated text, so that I can paste it into other applications. | Copy button for translated text. Text is copied to clipboard when clicked. Confirmation message (e.g. “Text copied”)
LTA-119 | As a diplomat, I want to have a "Microphone" button, so that I can record my voice input for translation without typing. |  |  | 3
| Microphone Button for Voice Input | Given I am a diplomat, I want to have a "Microphone" button, so that I can record my voice input for translation without typing. | A "Microphone" button is available for starting voice recording. Clicking the "Microphone" button begins recording the user's audio input. The system stops recording when the button is clicked again or a time limit is reached.
LTA-124 | As a lawyer, I want to be informed if my audio recording exceeds a certain time limit, so that I can manage the length of my input and avoid losing the recording. |  |  | 2
| Audio Input Time Limitation | Given I am a lawyer, I want to be informed if my audio recording exceeds a certain time limit, so that I can manage the length of my input and avoid losing the recording. | The system enforces a maximum recording time (e.g., 2 minutes). An error message or notification is shown if the user exceeds the recording limit.
LTA-120 | As a doctor, I want the system to accurately translate my recorded audio into another language, so that I can understand the content in a different language. |  |  | 5
| Accurate Translation of Audio Input | Given I am a doctor, I want the system to accurately translate my recorded audio into another language, so that I can understand the content in a different language. | The system processes the recorded audio and translates it into the selected target language. The translation is displayed after processing is completed. The translation reflects the meaning of the original audio input as accurately as possible.
LTA-122 | As an elderly user, I want to see visual indicator during the audio recording, so that I know when my voice is being recorded. |  |  | 2
| Audio Recording Indicator | Given I am an elderly user, I want to see visual indicator during the audio recording, so that I know when my voice is being recorded. | A visual indicator (such as a blinking icon or sound wave animation) is displayed when the recording is in progress. The indicator stops when the recording is finished or cancelled.
LTA-126 | As a student, I want a dropdown menu for selecting the output language, so that I can receive translations in any language of my choice. |  |  | 2
| Dropdown for Output Language Selection | Given I am a student, I want a dropdown menu for selecting the output language, so that I can receive translations in any language of my choice. | A dropdown menu is available next to the output field for selecting the output language. The dropdown displays a list of available languages for the user to choose from. The user can select any language from the list as the output language.
LTA-131 | As a multilinguistic, I want the system to save all my past translations, so that I can access my full translation history at any time. |  |  | 3
| Ability to Save All Past Translations | Given I am a multilinguistic, I want the system to save all my past translations, so that I can access my full translation history at any time. | The system automatically saves all translations made by the user. Users can access their full history of past translations from a dedicated section (e.g., "Translation History"). Past translations are stored persistently across sessions, allowing users to revisit them later.
LTA-129 | As a patient, I want to download the translated text in different file formats (e.g., .txt, .docx), so that I can choose the format that best suits my needs. |  |  | 2
| Supported Formats for Downloaded File | Given I am a patient, I want to download the translated text in different file formats (e.g., .txt, .docx), so that I can choose the format that best suits my needs. | The system offers options to download the translated content in supported formats such as .txt and .docx. The downloaded file contains the translated text in the chosen format.
LTA-128 | As a working professional, I want a "Download" button next to the translated text, so that I can download and save the translated content for future use. |  |  | 2
| Download Button for Translated Text | Given I am a working professional, I want a "Download" button next to the translated text, so that I can download and save the translated content for future use. | A "Download" button is displayed next to the translated text. Clicking the "Download" button triggers the download of the translated content.
LTA-151 | As a team, we want to make necessary modifications in our project as per professor’s feedback so that we deliver better presentation next sprint |  |  | 1
| Improvement Feedback from Sprint 1 | Given we are a team, we want to make necessary modifications in our project as per professor’s feedback so that we deliver better presentation next sprint
LTA-149 | As a team member, I want to update the wiki page with our current deliverable so that customers can checkout our current progress for this sprint |  |  | 2
| Wiki Page for Sprint 2 | Given I am a team member, I want to update the wiki page with our current deliverable so that customers can checkout our current progress for this sprint
LTA-148 | As a client, I want to like to know more about the product through a detailed technical paper so that I can have documented understanding of the product. |  |  | 5
| Technical Report | Given I am a client, I would like to know more about the product through a detailed technical paper so that I can have documented understanding of the product.
LTA-130 | As an accountant, I want to be able to reuse my past translations, so that I can revisit previous translations without re-entering the same text. |  |  | 3
| Ability to Reuse Past Translations | Given I am an accountant, I want to be able to reuse my past translations, so that I can revisit previous translations without re-entering the same text. | Users can view a list of their past translations. Users can select any past translation from the list to reuse it. The system automatically populates the input and output fields with the previously translated content when selected.
LTA-137 | As a frequent user, I want to access my profile and settings through dropdown menus on the right side of the header, so that I can manage my account and customize my preferences easily. |  |  | 2
| Dropdown Menus for Profile and Settings | Given I am a frequent user, I want to access my profile and settings through dropdown menus on the right side of the header, so that I can manage my account and customize my preferences easily. | A "My Profile" dropdown is available on the right side, providing access to user profile details. A "Settings" dropdown is present on the right side, offering options such as language and theme settings. Dropdown menus expand when clicked and collapse when not in use.