## Sheet1
| SPEAKEZ USER STORIES / SPRINT 1 | SPEAKEZ SPRINT 1 USER STORIES
Point estimated | As a | I want | So that | Feature
2 | User | to have an "Upload" button. | I can easily select and upload a file for translation. | Upload Button
3 | User | to see the progress of a file upload for translation . | I know when the upload is completed and the file is ready for translation. | Progress Indicator
3 | User | to be notified about the progress of the audio file transcription. | I know the transcription is complete and ready for use. | Progress Indicator
2 | User | to copy the transcribed text from the text box,. | I can use the transcription in other applications. | Copy Button
5 | User | the transcribed text to be displayed in a text box after I upload an audio file. | I can view the transcription easily. | Text box
3 | Developer | to ensure the Worker handles and processes messages from the Whisper model in correct order. | the transcription tasks are processed accurately and sequentially. | Worker Queue System
3 | Developer | to send the audio data to the Whisper model for transcription. | I can obtain the transcribed text from the audio. | Whisper Model
3 | Developer | to be able convert audio files into audio data. | the data can be processed for transcription by the Whisper model. | Whisper Model
5 | Developer | to implement worker functionality to handle incoming messages from the Whisper model. | the system can process audio transcription requests efficiently in the background. | Worker Functionality
5 | Developer | to configure the integration with the AI model to process user audio or file input and display the translated output. | users can submit non-text inputs and receive an accurate translation. | AI Model
1 | User | to see a header at the top of the page with a logo on the left. | I can easily identify the tool's branding. | Header with Logo
3 | User | a dropdown menu for selecting the input language. | I can choose any available language for translation. | Dropdown Menu
3 | User | to select the languages for translation before recording audio. | I can ensure the translation is done between my preferred languages. | Dropdown Menu
2 | User | to be able to confirm or cancel my voice input after recording. | I can ensure the correct input is used for translation. | Confirm / Cancel buttons