## Sheet1
		SPEAKEZ USER STORIES / SPRINT 2

User Story ID	Point estimated	As a(n)	I want	So that	Feature
LTA-138	5	Admin	to configure the Firebase database by following the provided UML diagram	the database structure aligns with the system’s requirements and functions efficiently.	Configure Firebase Database Based on UML Diagram
LTA-118	2	Customer	to be informed if the file I upload exceeds the size limit	I can upload a smaller file or take appropriate action.	File Size Limitation
LTA-116	1	Student	to see an error message when I upload an unsupported file type	I am informed about the file type restrictions and can take corrective action.	Error Message for Unsupported File Types
LTA-127	3	Teacher	to quickly copy the translated text	I can paste it into other applications.	Copy Translated Text
LTA-119	3	Diplomat	to have a "Microphone" button	I can record my voice input for translation without typing.	Microphone Button for Voice Input
LTA-124	2	Lawyer	to be informed if my audio recording exceeds a certain time limit	I can manage the length of my input and avoid losing the recording.	Audio Input Time Limitation
LTA-120	5	Doctor	the system to accurately translate my recorded audio into another language	I can understand the content in a different language.	Accurate Translation of Audio Input
LTA-122	2	Elderly user	to see visual indicator during the audio recording	I know when my voice is being recorded.	Audio Recording Indicator
LTA-126	2	Student	a dropdown menu for selecting the output language	I can receive translations in any language of my choice.	Dropdown for Output Language Selection
LTA-131	3	Multilinguistic	the system to save all my past translations	I can access my full translation history at any time.	Ability to Save All Past Translations
LTA-129	2	Patient	to download the translated text in different file formats (e.g., .txt, .docx)	I can choose the format that best suits my needs.	Supported Formats for Downloaded File
LTA-128	2	Working Professional	a "Download" button next to the translated text	I can download and save the translated content for future use.	Download Button for Translated Text
LTA-151	1	Team	make necessary modifications in our project as per professor’s feedback	we deliver better presentation next sprint	Improvement Feedback from Sprint 1
LTA-149	2	Team Member	update the wiki page with our current deliverable	customers can checkout our current progress for this sprint	Wiki Page for Sprint 2
LTA-148	5	Client	like to know more about the product through a detailed technical paper	I can have documented understanding of the product.	Technical Report
LTA-130	3	Accountant	to be able to reuse my past translations	I can revisit previous translations without re-entering the same text.	Ability to Reuse Past Translations
LTA-137	2	Frequent user	to access my profile and settings through dropdown menus on the right side of the header	I can manage my account and customize my	Dropdown Menus for Profile and Settings